## Sheet1
Release_Number | S_No | Planning_Element | Question_No | Task_Owner_Contributing_Role | Impact_Analysis_Question | Response | Justification_or_Implementation_Details | Target_Completion_Workflow_Phase
GA2.1.6 | 1 | CHANGE IMPLEMENTATION BACKLOG | -- | Change Owner or Design Owner | Are there any design change implementation backlog? Identify any open (not COMPLETE) MR/ECR/ECO that must be RELEASED or IMPLEMENTED for this ECR to move forward. When multiple open MR/ECR are listed or when backlog impacts multiple sites, recommend documenting implementation strategy based on approved part disposition (e.g., sequence in which design change should be released or implemented) | NO | No open and not completed MR/ECR/ECO is pending prior to this Design change.
GA2.1.6 | 2 | DESIGN HISTORY FILE | 1 | Engineering Representative | Does this design change require Product DHF (for the Products impacted by the proposed Design Change) to be updated? For example, Revise established product DHF Index if applicable. | YES | Update IPM DHF Index DOC2275693 for this Design Change release | PRIOR TO ECO RELEASE
GA2.1.6 | 3 | DESIGN INPUT | 2 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to "DESIGN INPUT" design controls element? If NO, document the rationale for no impact. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)". There is no change to the Design Input | PRIOR TO ECO RELEASE
GA2.1.6 | 4 | DESIGN INPUT | 2.1 | Engineering Representative | Does this design change add or remove target markets and countries (e.g., impact on FDA, EU MDD/MDR, labeling and language requirements), requiring Design Input Requirements update? | NO | No change in Target Market and counties for this design change. This release Scope is limited to items referenced in "SW Change Set (Scope-Impact) sheet only".
GA2.1.6 | 5 | DESIGN INPUT | 2.2 | Engineering Representative Clinical Representative | Does this design change impact released Product User Needs and Intended Uses requirements included/referenced in DHF? | NO | No Change to User requirements for this DCP
GA2.1.6 | 6 | DESIGN INPUT | 2.3 | Engineering Representative | Does this design change Impact released Product Performance and Functional design requirements (system/subsystem/component level requirements) included/referenced in DHF? | NO
GA2.1.6 | 7 | DESIGN INPUT | 2.4 | Engineering Representative | Does this design change Impact product compatibility requirements (addition or removal of compatible devices or accessories)? | NA | Not applicable for SaaS based Cloud environement product. No hardware and accessories applicable for Cloud environement product.
GA2.1.6 | 8 | DESIGN INPUT | 2.5 | Engineering Representative | Does this design change impact Product Standards design input requirements that apply to features, technology for the identified target markets and countries (e.g., IEC60601-1, ISO 10933, WEEE, RoHS, Batteries, Telecommunication, Wi-Fi, Bluetooth)? | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 9 | DESIGN INPUT | 2.6 | Engineering Representative | Does this design change impact applicable internal GEHC Global Requirements Specifications per GEHC_GQP_10.01.003_F001 GEHC Global Requirements Specifications Form (DOC2299885) established as part of product realization, for the product in scope? NOTE: The completed product GEHC Global Requirements Specifications Form is maintained in Product DHF Index. | NO | This change has no impact on GEHC Global Requirements Specifications. This release Scope is limited to items referenced in "SW Change Set (Scope-Impact) sheet only".
GA2.1.6 | 10 | DESIGN INPUT | 2.7 | Service Representative Installation Representative | Does this design change impact released Installation or Service requirements (e.g., Installation, Maintenance and Repair, Tools, Diagnostic requirements, siting requirements)? If YES QS_1001_T001 Product Service Standards Assessment Summary and Justification Template (DOC2449236) should be reviewed/updated with the new requirements NOTE: Confirm if there are changes to the customer site requirements/customer room preparation, change to the PIM (Pre-Installation Manual) as it may in turn drive changes to GE Design Center content and ultimately customers who currently are reviewing drawings, budgeting for siting requirements and/or currently building their room. NOTE: Refer to QS_1001 Global QS Standard WI for Product Service Standards (DOC0487759) for further guidance | NO | No changes to installation or service requirements.
GA2.1.6 | 11 | DESIGN INPUT | 2.8 | Engineering Representative | Does this design change impact Packaging requirements? (e.g., size, weight, storage, shelf life, packaging material, special handling)? | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 12 | DESIGN INPUT | 2.9 | Manufacturing Representative | Does this design change impact Manufacturing/manufacturing environment requirements (based on manufacturing capabilities and needs)? | NO | this change is done in a non impacted Cloud environement.
GA2.1.6 | 13 | DESIGN INPUT | 2.10 | Sourcing Representative | Does this design change impact Sourcing requirements (e.g., based on supplier capabilities and needs)? | Yes | Update Program Sourcing Plan DOC2102789 to reflect change/addition of SUSE SLES 15SP4. | PRIOR TO ECO RELEASE
GA2.1.6 | 14 | DESIGN INPUT | 2.11 | Engineering Representative Product Security Leader | Does this design change impact Product Privacy and Security requirements (e.g., Cyber threat model and controls, access controls, network and data security controls, product privacy and security manual instructions)? | NO | No update to Security threat models identified for this release as per scope items referenced in "SW Change Set (Scope-Impact)" worksheet.
GA2.1.6 | 15 | DESIGN INPUT | 2.12 | Engineering Representative | Does this design change impact electronic interface interoperability requirements (e.g., DICOM, IHE, HL7 conformance)? NOTE: Refer to QS_5001 Global Standard WI for Conformity with Recognized Medical Interoperability Standards (DOC2432296) for further guidance | NA | IPM is SaaS based protocol management Cloud environment application and does not deal with any of interoperability related requirements like DICOM, IHE, HL7 conformance. Hence, this is NOT APPLICABLE
GA2.1.6 | 16 | DESIGN INPUT | 2.13 | Engineering Representative | If any other inputs are impacted, identify impacted work products and implementation task required. | NO | No other inputs are impacted for this release.
GA2.1.6 | 17 | RISK MANAGEMENT | 3 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to RISK MANAGEMENT design controls element? If NO, document the rationale for no impact. | NA | Scope limited to items referenced in "SW Change Set (Scope-Impact)". There is no change to risk management files as IPM application is non-medical device. RISK MANAGEMENT is not applicable as per Product Determination and classification document DOC1919713 REV7. Hence there is no RAC, CMT associated for the IPM program. IPM solution is being developed with Class A development rigor. There are no risk and hazards associated with IPM application.
GA2.1.6 | 18 | RISK MANAGEMENT | 3.1 | Engineering Representative | Does this design change impact existing risk mitigations, or identify the need for additional risk mitigation requiring verification and/or validation activities? | NA | Not Applicable as IPM is a non-medical device as per the IPM Product Determination and Classification doc DOC1919713 REV7.
GA2.1.6 | 19 | RISK MANAGEMENT | 3.2 | Engineering Representative | Does this design change introduce new hazards or new causes, and impacts change to the residual risk(s) or their acceptability? | NA | Not Applicable as IPM is a non-medical device as per the IPM Product Determination and Classification doc DOC1919713 REV7.
GA2.1.6 | 20 | RISK MANAGEMENT | 3.3 | Engineering Representative Risk Management Representative | Does this design change implementation require updates to Risk Assessment and Control Document (RAC), Product Cause and Mitigation Table (CMT)? | NA | IPM is a non-medical device as per the IPM Product Determination and Classification doc DOC1919713 REV7. Hence there is no RAC, CMT associated for the IPM program. Not Applicable.
GA2.1.6 | 21 | RISK MANAGEMENT | 3.4 | Engineering Representative | Does this design change add or change Design Input or other requirements traced to Essential Characteristic or finished Design Output? If Yes, assess impact to product RMF deliverables | NA | Not applicable as IPM is a SaaS based Cloud environement product.
GA2.1.6 | 22 | RISK MANAGEMENT | 3.5 | Engineering Representative | Does this design change impact software classified as Class B or C? If Yes, access impact to product RMF deliverables | NA | IPM is a non-medical device as per the IPM Product Determination and Classification doc DOC1919713 REV7. IPM solution is being developed with Class A development rigor. Hence, there are no software moduls classfied as Class B or C.
GA2.1.6 | 23 | RISK MANAGEMENT | 3.6 | Engineering Representative | Does this design change introduce new product feature or functionality? If Yes access impact to product RMF deliverables | NA | Not applicable as IPM is a SaaS based Cloud environement product.
GA2.1.6 | 24 | RISK MANAGEMENT | 3.7 | Engineering Representative | Does this design change introduce change to material that is either non-equivalent to the existing material and/or has patient contact (i.e., Biocompatibility)? If Yes, access impact to product RMF deliverables | NA | Not applicable as IPM is a SaaS based Cloud environement product.
GA2.1.6 | 25 | RISK MANAGEMENT | 3.8 | Engineering Representative | Does this design change add or introduce change to Essential Part (including labeling) and essential controls? If Yes, access impact to product RMF deliverables | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 26 | RISK MANAGEMENT | 3.9 | Engineering Representative | Does this design change impact product Expected Service Life evaluated and documented in Product Risk Management File/Standard Conformance (Ref: IEC 60601-1 Clause 4.4)? | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 27 | Failure Modes and Effects Analysis | 4 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to FMEA process? If NO, document the rationale for no impact. Refer to GEHC_GQP_08.01 Risk Management Procedure (DOC0283944) for FMEA Templates & minimum requirements Refer to Failure Modes and Effects Process Standard (DOC2433962) for further guidance | NA | Scope limited to items referenced in "SW Change Set (Scope & Impact)". No new FMEA were identified
GA2.1.6 | 28 | Failure Modes and Effects Analysis | 4.1 | Usability Representative | Does this design change impact released Task Analysis or Use Failure Mode and Effects Analysis (UFMEA) or requires creation of new UFMEA? | NO | No new UFMEA are identified for this release as per scope defined in "SW Change Set (Scope-Impact)" sheet.
GA2.1.6 | 29 | Failure Modes and Effects Analysis | 4.2 | Engineering Representative | Does this design change impact released Design FMEA (or other tools/methods, e.g., FTA, Engineering review and/or analysis) or requires developing new DFMEA records? | NO | No new FTA or other tools /methods are identified for this release as per scope defined in "SW Change Set (Scope-Impact)" sheet.
GA2.1.6 | 30 | Failure Modes and Effects Analysis | 4.3 | Manufacturing Representative | Does this design change impact released Process FMEA for manufacturing and/or used medical device processing or requires development of new PFMEA records? | NO | This change do not modify the Cloud process
GA2.1.6 | 31 | Failure Modes and Effects Analysis | 4.4 | Service Representative Installation Representative | Does this design change impact released Process FMEA for service, installation/de-installation/upgrade or requires development of new PFMEA records for service/installation/maintenance? | NO | Service is not impacted by this DCP, hence, no new PFMEA need to be introduce for this DCP release.
GA2.1.6 | 32 | Failure Modes and Effects Analysis | 4.5 | Service Representative Installation Representative | Does this design change affect distribution processes requiring special handling (i.e., not able to be transported via general cargo) OR Impacts distribution PFMEA? NOTE: Distribution includes packaging, transportation, and storage. | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 33 | REGULATORY ASSESSMENT | 5 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to product REGULATORY design controls element? If NO, document the rationale for no impact. | YES | Not Applicable, since there is no change in regulatory requirement. The IPM application is a non-medical device Cloud based product. The product determination for IPM application remains unchanged for this release. Regulatory clearance for this release is not needed per Product Determination DOC1919713. | PRIOR TO ECO RELEASE
GA2.1.6 | 34 | REGULATORY ASSESSMENT | 5.1 | Regulatory Affairs Representative Quality Representative | Does this design change represent Substantial/Significant Change to quality processes or product required per GEHC_GQP_03.01_Quality Plan Procedure (DOC0289782) and warrants communication to Notified Body (NB). | NA | The IPM application is a non-medical SaaS based Cloud environment product.
GA2.1.6 | 35 | REGULATORY ASSESSMENT | 5.2 | Regulatory Affairs Representative | Does this design change impact Regulatory certifications/registrations/licenses of the end use products? e.g., AERB, CE mark, Health Canada license, China NMPA certs/PTR, country specific license/registrations, Notified body certification (TÜV, BSI, GMED, CSA, UL, etc.)? | NA | The IPM application is a non-medical SaaS based Cloud environment product. No new Regulatory certification, registration, licenses of the end products are required. The product determination and classification for IPM application remains unchanged for this release.
GA2.1.6 | 36 | REGULATORY ASSESSMENT | 5.3 | Engineering Representative | Does this design change impact Labeling (e.g., updates to system labels, rating plates, regulatory/safety labels, instructions for use, indications for use, addition/deletion of contraindications, GTIN)? NOTE: Change in rating plate may have UDI implications (if it is a new medical device, ensure the medical device is structured at or below the rating plate level in the BOM). | YES | IPM User Manualand PSM will be updated as part of this DCP release. | PRIOR TO ECO RELEASE
GA2.1.6 | 37 | REGULATORY ASSESSMENT | 5.4 | Engineering Representative | Does this design change impact the control mechanism, operating principle, energy type, main electrical ratings, or certification and testing standards? | NO | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 38 | REGULATORY ASSESSMENT | 5.5 | Engineering Representative | Does this design change impact sterile components, sterile packaging, sterilization methods or changes in biological material of the device? | NO | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 39 | REGULATORY ASSESSMENT | 5.6 | Manufacturing Representative | Does this design change impact procedures, product manufacturing processes, test specifications/reports, etc. that have regulatory impact? | NO | This change do not imply any procedure nor process modification.
GA2.1.6 | 40 | REGULATORY ASSESSMENT | 5.7 | Engineering Representative | Does this design change impact regional regulatory requirements and safety standards? | NA | The IPM application is a non-medical SaaS based Cloud environment product. No new Regulatoryrequirements are required. The product determination and classification for IPM application remains unchanged for this release. This design change is not applicable.
GA2.1.6 | 41 | REGULATORY ASSESSMENT | 5.8 | Engineering Representative | Does this design change affect MDD/MDR technical file, Declaration of Conformity, 510(k) claims, PMA device, Letter to File, essential principles, annual reports, product report, GSPR, or EU DoC? | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 42 | REGULATORY ASSESSMENT | 5.9 | Regulatory Affairs Representative | Does this change require the completion of the MDR Significant Change Assessment Form (DOC2193466)? Select appropriate. 1.No.Not Applicable – Product is a Class I product and EU MDR Compliant 2.No: Not Applicable –Product is a Class II product and EU MDR compliant 3.No: Not Applicable – Change does not impact the CE Marked elements of a device (changes to regional device labels outside of the EU – not applicable if changing the device label that bears the CE Mark) 4.No: Not Applicable – Non-significant change based on scope (Changes that do not impact the product such as addition of secondary source supplier, documentation error fixes, component obsolescence change that is not impact form fit and function)" 5.Yes: Attributes as per Chart M of DOC2193466 are impacted. Need evidence of Change assessment form completion either attached to ECO or separate document. | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. MDR is not applicable.
GA2.1.6 | 43 | REGULATORY ASSESSMENT | 5.10 | Regulatory Affairs Representative | Does this design change impact established regulatory compliance plan (RCP) or post commercial release RA strategy? | NA | The IPM application is a non-medical SaaS based Cloud environment product. No new Regulatoryrequirements are required. The product determination and classification for IPM application remains unchanged for this release. This design change is not applicable.
GA2.1.6 | 44 | REGULATORY ASSESSMENT | 5.11 | Regulatory Affairs Representative | Does this design change Introduce new commercial catalogs or offerings, requiring RA action? | NO | No new commercial offering or new catalogs are introduced for this design change.
GA2.1.6 | 45 | REGULATORY ASSESSMENT | 5.12 | Regulatory Affairs Representative | Does this design change introduce new accessory that was not previously registered with the device? NOTE: Adding a new medical device accessory according to MDR might trigger RA action. | NA | The IPM application is a non-medical SaaS based Cloud environment product. No new Regulatoryrequirements are required. The product determination and classification for IPM application remains unchanged for this release. This design change is not applicable.
GA2.1.6 | 46 | REGULATORY ASSESSMENT | 5.13 | Regulatory Affairs Representative | Assessment required per DOC0860577 Global RA Change Assessment Guide? | NO | The IPM application is a non-medical SaaS based Cloud environment product. No new Regulatoryrequirements are required. The product determination and classification for IPM application remains unchanged for this release. This design change is not applicable.
GA2.1.6 | 47 | REGULATORY ASSESSMENT | 5.14 | Engineering Representative | Does this design change introduce change to ergonomics, software/firmware, environmental, performance or dimensional specifications? If yes, does this change require the need for clinical data to establish safety and effectiveness or result in design validation that raises new issues of safety and effectiveness? | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 48 | REGULATORY ASSESSMENT | 5.15 | Engineering Representative Regulatory Affairs Representative | Does this design change include FMI/safety fixes (reportable in any country)? If yes, identify action to perform post market assessment. | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. FMI is not applicable.
GA2.1.6 | 49 | REGULATORY ASSESSMENT | 5.16 | Engineering Representative | Other, identify impacted work products and implementation task required. | NO | No other work products and implementation task are required as per scope defined in "SW Change Set (Scope-Impact)" sheet.
GA2.1.6 | 50 | DESIGN OUTPUT | 6 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to DESIGN OUTPUT design controls element? If NO, document the rationale for no impact. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and refer to VnV Plan & Reports for List of Design Output document updates. | PRIOR TO ECO RELEASE
GA2.1.6 | 51 | DESIGN OUTPUT | 6.1 | Marketing Representative | Does this design change Modify or releases a new commercial offering identified in PCM (Product Configuration Master), ACM (Accessories Configuration Master), ATO (Assemble To Order), PTO (Pick To Order) etc.? | NO | No change in the PCM , ACM, ATO and PTO for this design change release.
GA2.1.6 | 52 | DESIGN OUTPUT | 6.2 | Engineering Representative | Does this design change Impact part(s) that are classified as a GEHC Medical Device? AND the proposed change: Modifies Brand name, Model name OR... modifies UDI published attributes (Product Model number, Manufacturer…) OR... modifies quantity of mandatory component OR... replaces/removes mandatory component OR... changes/removes language from system’s user interface/outputs, labeling, documentation or packaging OR... changes Part Number of Medical Device OR... changes/new medical device identification (certification, registration, regulatory labeling) | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 53 | DESIGN OUTPUT | 6.3 | Engineering Representative Configuration Management Specialist/Leader | Does this design change Impact any of the Product Controllership attributes including UDI? (including a change to BOM/Collector BOM/Parent Catalog that impacts medical device offerings, or upgrades/replacement parts) | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 54 | DESIGN OUTPUT | 6.4 | Engineering Representative | Does this change impact I&T (identification and traceability) items? If yes, list impacted I&T part and related I&T Part list document that needs to be revised if applicable, and confirm if this item need to be tracked in global tracking system. (Refer to GEHC_GQP_12.04 Identification and Traceability Procedure (DOC0373356) for further guidance) | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 55 | DESIGN OUTPUT | 6.5 | Marketing Representative | Does this design change impact Global Data Synchronization Network (GDSN)/GTIN,Commercial Identifiers, Promotional Materials/Brochures, Impact on User Needs and Intended Uses, Product appearance and Product cost? If Yes, confirm with Marketing for any actions to be completed prior to implementation | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 56 | DESIGN OUTPUT | 6.6 | Engineering Representative Product Security Leader | Does this design change impact Cybersecurity Design Output deliverables: Impacts existing or requires new cybersecurity deliverables (e.g., DEPS Controls Baseline Catalog, Threat Model, SRA, PIA, MMSR, or Security Assessment Summary)? If yes, ensure PSR/PSL approvals are obtained as applicable | YES | Security Assessment Summary document will be updated for this design change release. | PRIOR TO ECO RELEASE
GA2.1.6 | 57 | DESIGN OUTPUT | 6.7 | Engineering Representative Product Security Leader | Does the design output updates in scope of this design change introduce new cybersecurity vulnerabilities that need to be assessed? Or are there any cybersecurity improvements that need to be implemented with this change? | YES | SAST and DAST assessments will be performed for this design change release. | PRIOR TO ECO RELEASE
GA2.1.6 | 58 | DESIGN OUTPUT | 6.8 | Engineering Representative | Does this design change impact released Design Specifications (Finished design outputs from design phase) e.g., ADW/DDW/PSP/TST, requiring update? | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 59 | DESIGN OUTPUT | 6.9 | Engineering Representative | Does this design change impact Bill of Materials for an assembly? If so, the assembly needs to be assessed for opportunities to use standard parts, using the Managed Library Report. See DOC2289045 GEHC Component Selection Guidance | NA | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 60 | DESIGN OUTPUT | 6.10 | Service Representative | Does this design change impact released product Service Manuals or documentation, e.g., service Tech Pub Labeling? For example, impact to a FRU/DRU part number or service instructions. Refer to Global QS Std WI for Technical Publications (DOC2139328) for further guidance | YES | IPM Service Manual, Technical Overview & Customer IT, Service Release Note Requirments will be updated for this DCP release | PRIOR TO ECO RELEASE
GA2.1.6 | 61 | DESIGN OUTPUT | 6.11 | Installation Representative | Does this design change impact released product Installation manual/Pre-installation/de-installation/upgrade documentation (siting requirements, design center blocks and templates, customer drawings)? | YES | IPM Service Manual will be impacted for this design change. | PRIOR TO ECO RELEASE
GA2.1.6 | 62 | DESIGN OUTPUT | 6.12 | Manufacturing Representative | Is "on-product labeling" printed in-process using a Software program (e.g., BarTender)? If so, does this change impact the following: - Dynamic fields - Static fields - Part verification or manufacturing process validation (e.g., printed label) | NA | this change is done in a non impacted Cloud environement. Nothing to print.
GA2.1.6 | 63 | DESIGN OUTPUT | 6.13 | Engineering Representative | Does this design change impact released On Product Labeling/Operator/User Manuals (including addendums, datasheet, brochure or any other user facing instructions), e.g., User Tech Pub or Product Labeling/Documentation (Instructions for Use (IFU), translated addendums), product rating plate label, UDI label? | YES | IPM User Manual will be updated for this design change. | PRIOR TO ECO RELEASE
GA2.1.6 | 64 | DESIGN OUTPUT | 6.14 | Engineering Representative | Does this design change impact existing Field Replaceable Units (FRU) and/or Depot Replaceable Units (DRU) setup? Does this change require updates in iSpare for example? Is Technical nature attribute set up under classification power view with respect to part nature for Spare Parts? | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 65 | DESIGN OUTPUT | 6.15 | Engineering Representative Regulatory Affairs Representative | Does this design change Modify or releases new accessory(s)? [Pre-qualified accessories, accessories that can be connected to or interact with the medical device/product may require engineering review to determine need for technical justification or full verification testing or full validation testing, i.e., reference the testing or justification and DHF documentation updates for biocompatibility, safety, EMC, design verification for compatibility, etc.] | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 66 | DESIGN OUTPUT | 6.16 | Engineering Representative Regulatory Affairs Representative | Is there any change that alters established method of compliance to the basic safety and essential performance requirements in the standard? Part(s) in scope of this change is a critical component? Does this Design Change impact NRTL Listing Report/safety standard test reports, CB Certification and Critical Component List? Example: Impact NMPA registration, PTR (Product Technical Requirement) and PTR mapping to design control and production control | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 67 | DESIGN OUTPUT | 6.17 | Manufacturing Representative | Does this design change impact a harvested part? Is there an impact to established Harvesting WI, SOP, or process document for the product? | NA | Not applicable for Cloud environement product
GA2.1.6 | 68 | DESIGN OUTPUT | 6.18 | Engineering Representative | Does this design change impact EMI/EMC certifications reports, Suspended Masses, Actual Or Possible Harm To Patient, User, or Service Personnel, etc.? | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 69 | DESIGN OUTPUT | 6.19 | Engineering Representative | Does this design change impact compliance of WEEE passport(s), RoHS or REACH, Phthalate, DEHP (France), Proposition 65 status, EU_EEA Restriction in use of PFOA, its salts and PFOA-related compounds? | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 70 | DESIGN OUTPUT | 6.20 | Engineering Representative | Does this design change impact Battery or Battery report? (added/changed/removed/restructured) | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 71 | DESIGN OUTPUT | 6.21 | Engineering Representative | Does this design change impact Chemical, Physical, Biological characteristics/properties? | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 72 | DESIGN OUTPUT | 6.22 | Engineering Representative | Does this Design Change impact product appearance? If yes, describe change to product appearance and confirm if review/approval from Industrial design team/representative is required. | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 73 | DESIGN OUTPUT | 6.23 | Engineering Representative | Is the affected part(s) essential characteristics control plan impacted? OR...Are any of the Parts converted from Non-Essential to Essential classification? OR...Are any design output essential characteristics being changed as a result of the design change? OR...Are NEW parts classified as Essential added to Bill Of Materials (BOM)? NOTE: Document the rationale for changing legacy safety /function/Essential part to Non-Essential. | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 74 | DESIGN OUTPUT | 6.24 | Engineering Representative | Does this design change impact Telecommunication Registrations and Certifications? (WiFi, UWB, Bluetooth, ZigBee, etc.). Refer to GEHC Engineering Standard for Wireless Product Compliance Planning (DOC2360208) for further guidance. | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 75 | DESIGN OUTPUT | 6.25 | Engineering Representative | Trade Compliance: Does this design change include a change to the Country Of Origin (COO) for an existing buy part? | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 76 | DESIGN OUTPUT | 6.26 | Engineering Representative | Is this design change associated with updates to Alternate/Substitue parts? If yes consider all aspects of use (e.g., service, software impact) and identify actions to ensure traceability throughout the entire lifecycle of the product | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 77 | DESIGN OUTPUT | 6.27 | Engineering Representative | Does this design change impact Seismic certifications or have seismic design impact? If YES, indicate required tasks to complete. | NO | The IPM application is a non-medical SaaS based Cloud environment product with Class A classifiation. This design change is not applicable.
GA2.1.6 | 78 | DESIGN VERIFICATION | 7 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to DESIGN VERIFICATION design controls element? If NO, document the rationale for no impact. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Verification report will be updated post formal verification cycle. Refer VnV Plan & Report sheet for more details. | PRIOR TO ECO RELEASE
GA2.1.6 | 79 | DESIGN VERIFICATION | 7.1 | Engineering Representative | Does this design change impact design inputs (new or existing) requiring verification to confirm that specified requirements are met, mitigations are effective, and that no unintended consequences have been introduced as a result of the design change? NOTE: Verification Plan may be identified as a required work product to be completed at ECR phase or identified as a supporting evidence along with verification results. NOTE: Update to Traceability of Design Input and lower-level requirements to associated Design Verification activities and results may be required. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Verification report will be updated post formal verification cycle. Refer VnV Plan & Report sheet for more details. | PRIOR TO ECO RELEASE
GA2.1.6 | 80 | DESIGN VERIFICATION | 7.2 | Engineering Representative | Does this design change require compatibility testing to confirm forward/backward compatibility of proposed design change with other systems, products, or interfaces? | NO | Not applicable for SaaS based Cloud environement product. Since there is no backward software deployed in cloud environment.
GA2.1.6 | 81 | DESIGN VERIFICATION | 7.3 | Engineering Representative | Does this design change require verification regression testing? | YES | Solution Verification Steering Guide will be prepared updated in later revision of this document during ECO. | PRIOR TO ECO RELEASE
GA2.1.6 | 82 | DESIGN VERIFICATION | 7.4 | Engineering Representative | Does this design change require technical analysis/specification analysis (e.g., scenarios where there is no impact to product design, however require engineering analysis to confirm this as part of justification) NOTE: Expert Evaluation and Analysis, including Technical Design Review, FMEA, FTA, and retrospective analysis of historical data applicable to the current design is one of the verification method and technique, per Verification GWI | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)". FMEA document will be updated prior ro release of Eco | PRIOR TO ECO RELEASE
GA2.1.6 | 83 | DESIGN VERIFICATION | 7.5 | Engineering Representative | Does this Design Change make a change to an accessory that would require a Compatibility Assessment with a host/impacted device? | NA | Not applicable for SaaS based Cloud environement product.
GA2.1.6 | 84 | DESIGN VERIFICATION | 7.6 | Engineering Representative | Does this design change impact Engineering test equipment, tools, simulators, software, product bays, products (used for testing/equipment qualification, etc.) used for engineering development requiring re-verification/revision/re-validation/qualification? | NO | Scope limited to items referenced in "SW Change Set (Scope & Impact)". There is no additional tool, simulator or equipment update is required for this release.
GA2.1.6 | 85 | DESIGN VALIDATION | 8 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to DESIGN VALIDATION design controls element? If NO, document the rationale for no impact. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Validation report will be updated post formal Validation cycle. Refer VnV Plan & Report sheet for more details. | PRIOR TO ECO RELEASE
GA2.1.6 | 86 | DESIGN VALIDATION | 8.1 | Engineering Representative | Does this design change impact design inputs (new or existing) requiring validation to confirm that the product continues to meet user needs and intended uses, mitigations are effective, and that no unintended consequences have been introduced as a result of the design change? NOTE: Validation Plan may be identified as a required work product to be completed at ECR phase or identified as a supporting evidence along with validation results. NOTE: Update to Traceability of Design Input requirements to associated Design Validation activities and results may be required. NOTE: Consider all user groups when evaluating impact to validation, i.e., Service, Clinical, etc. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Validation report will be updated post formal Validation cycle. Refer VnV Plan & Report sheet for more details. | PRIOR TO ECO RELEASE
GA2.1.6 | 87 | DESIGN VALIDATION | 8.2 | Engineering Representative | Does this design change require validation regression testing? | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Validation report will be updated post formal Validation cycle. Refer VnV Plan & Report sheet for more details. | PRIOR TO ECO RELEASE
GA2.1.6 | 88 | SOFTWARE | 9 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to SOFTWARE design controls element? If NO, document the rationale for no impact. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and Software Architecture Document will be updated Prior to release of this Design Change. | PRIOR TO ECO RELEASE
GA2.1.6 | 89 | SOFTWARE | 9.1 | Engineering Representative | Does this design change impact SOUP/third-party purchased software components? NOTE: If Yes, evaluate impact as per risk management and purchasing controls requirements. NOTE: If Yes, also verify to ensure that SOUP/third-party software functionality and no unintended side effects are introduced. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and required SOUP version will be updated prior to ECO release. | PRIOR TO ECO RELEASE
GA2.1.6 | 90 | SOFTWARE | 9.2 | Engineering Representative | Does the review of software (including SOUP) change determines whether: - Additional potential causes are introduced contributing to hazardous situations. - Additional risk mitigations are required. - The software change could interfere with existing risk mitigations. If Yes and there is an impact, identify relevant risk management activities based on impact of software design changes. | YES | Scope limited to items referenced in "SW Change Set (Scope & Impact)" and required SOUP version will be updated prior to ECO release. | PRIOR TO ECO RELEASE
GA2.1.6 | 91 | SOFTWARE | 9.3 | Engineering Representative | Does this design change require action per released product software maintenance plan (e.g., software architecture, SDD, software release, SOUP Index, software classification)? | NO | Software Architecture Document is not imapcted for this Design Change.
GA2.1.6 | 92 | SOFTWARE | 9.4 | Engineering Representative | Does this design change include software upgrades, bug fixes, or obsolescence of SOUP items requiring software testing to ensure no unintended side effects are introduced? | NO | No change for this release.
GA2.1.6 | 93 | SOFTWARE | 9.5 | Engineering Representative | Does this Design Change require released software validation test procedure to be executed to reestablish software validation? | NO | No change for this release.
GA2.1.6 | 94 | SOFTWARE | 9.6 | Engineering Representative | Does this Design Change require updates to licensing servers/activation code servers based on software versioning? | NO | No change for this release.
GA2.1.6 | 95 | SOFTWARE | 9.7 | Engineering Representative | Is this software change compatible with all older revision of hardware's in IB? Does this Design Change make a change to the Product Hardware that would require a System Compatibility Assessment? | NA | Not applicable for SaaS based Cloud enviroment product.
GA2.1.6 | 96 | SOFTWARE | 9.8 | Engineering Representative | Is this software change compatible with all older revision of software in IB? Does this Design Change make a change to the Product Software/Firmware that would require a System Compatibility Assessment/regression test? | NA | Not applicable for SaaS based Cloud enviroment product.
GA2.1.6 | 97 | USABILITY | 10 | Usability Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to USABILITY design controls element? If NO, document the rationale for no impact. | NO | Scope of this Design Change Release is limited to items as listed in "SW Change Set (Scope & Impact)" and there is no change in Usability design control for this release.
GA2.1.6 | 98 | USABILITY | 10.1 | Usability Representative | Does this design change impact Usability File Index (UFI) deliverables requiring update to UFI or Use Analysis Report (UAR)? | NO | No new User Feature added hence no change in Usablity applicable for this release.
GA2.1.6 | 99 | USABILITY | 10.2 | Usability Representative Clinical Representative | Does this design change impact released Device Use Definition (including intended use, patient population, user profile, use environment, and primary operating functions and/or associated Use Scenarios (per UAR))? NOTE: Usability applies to interactions among the patient, User, device, and Use Environment. NOTE: Consider all user groups when evaluating impact to usability, i.e., Service, Clinical, etc. | NO | No new User Feature added hence no change in Usablity applicable for this release.
GA2.1.6 | 100 | USABILITY | 10.3 | Usability Representative Clinical Representative | Does this design change impact Use-based hazards/risk mitigations and/or introduces new use-based hazards/risk mitigations? | NO | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 101 | USABILITY | 10.4 | Usability Representative | Does this design change impact Critical Task or identifies new Critical Task? | NO | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 102 | USABILITY | 10.5 | Usability Representative | Does this design change impact Formative Evaluations and/or Summative Usability testing? If Yes, Identify action to create Summative Testing Plan and/or Formative Evaluation Plan as applicable. | NO | No new User Feature added hence no change in Usablity applicable for this release.
GA2.1.6 | 103 | USABILITY | 10.6 | Usability Representative | Does this design change impact User Interface of Unknown Provenance (UOUP) and is UOUP objective evidence needed (Device Use Definition in Use Analysis Report and documentation of Use Errors identified in Post-Market Data, including, but not limited to complaints, hazardous investigations with root cause of Use Error, near misses, adverse events, and recalls)? | NO | No new User Feature added hence no change in Usablity applicable for this release.
GA2.1.6 | 104 | USABILITY | 10.7 | Usability Representative | Does this design change address Use Errors identified in complaints, adverse events, and/or recalls requiring a Known Use Problems evaluation? | NO | No new User Feature added hence no change in Usablity applicable for this release.
GA2.1.6 | 105 | DESIGN TRANSFER | 11 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to DESIGN TRANSFER design controls element? If NO, document the rationale for no impact. NOTE: It is recommended to use GEHC_GQP_10.01.007_T002 Design Transfer Plan Template (DOC2317856) for iteration and growth program. | YES | IPM application is a Non-Medical Cloud based SaaS application, and there is no design transfer to manufacturing, once ECO is released Dev Ops team deploys the binaries to respective production environments. Hence this is not applicable to IPM | PRIOR TO ECO RELEASE
GA2.1.6 | 106 | DESIGN TRANSFER | 11.1 | Service Representative | Does this design change impact Service Finished design outputs? (e.g., Service manuals, service notes, asset creation in the service CRM, service checklist, replacement procedures, spare parts list, tools, processes, UDI Label Instructions, technical bulletin) Refer to QS_4004 Global Standard Work Instruction for Item Creation (DOC2473345) for further guidance on asset creation in service CRM. | YES | IPM Service Manual, Technical Overview & Customer IT, Service Release Note Requirments will be updated for this DCP release | PRIOR TO ECO RELEASE
GA2.1.6 | 107 | DESIGN TRANSFER | 11.2 | Service Representative | Does this Design Change require Installation & Service Process Validation? If yes, provide the installation & service process validation plan/procedure document number, and complete validation prior to ECO implementation. | YES | Yes Service Validation will be occuring. | PRIOR TO ECO RELEASE
GA2.1.6 | 108 | DESIGN TRANSFER | 11.3 | Manufacturing Representative | Does this design change impact MAKE Parts? (i.e., Change to Manufacturing Process/Procedures/Work Instructions(WI)/OMS, SOP or require a New Process/Procedure, Process Validation, in-process label printing, testing, incoming, in-process, final acceptance, tooling, training, e.g., PPC or MVP), MTS, and PCL (Part Classification List) | YES | This change will impact SW PN and CAT# MAKE part. MR & ECO will be created. | PRIOR TO ECO RELEASE
GA2.1.6 | 109 | DESIGN TRANSFER | 11.4 | Environmental Health and Safety (EHS) Representative | Does this design change affect Environmental Health and Safety (EHS) or EHS evaluation? | NA | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 110 | DESIGN TRANSFER | 11.5 | Supplier Quality Representative | Does this design change require additional external Supplier Qualification or Notification (SCN) for affected parts? NOTE: Check if the ECR introduces parts from an external supplier that is not on the site ASL. NOTE: GEHC Initiated changes may require SCN (Supplier Change Notification) per GEHC_GQP_11.01.009 Purchasing Change Management Work Instruction (DOC0288388) NOTE: Check if SCN needs to be issued to suppliers tasked with procuring the affected parts, if this change is associated with MEP maintenance. | YES | Additional of Suse as a new supplier to IPM 2.1.6, qualification record will need to be updated with evidence of 1) “Proof of Ownership’ and 2) exemption of supplier from “Supplier Quality Requirements (SQR)” Agreement. | PRIOR TO ECO RELEASE
GA2.1.6 | 111 | DESIGN TRANSFER | 11.6 | Sourcing Representative Materials Representative | Does this design change impact a part that is EOL (End Of Life) requiring LTB (Last Time Buy) action to be initiated or assessed? | NO | No EOL or LTB
GA2.1.6 | 112 | DESIGN TRANSFER | 11.7 | Manufacturing Representative | Does this design change require Incoming Material Qualification for BUY Parts (Manufacturing and Drop Ship)? Does Incoming acceptance document (e.g., ITD), Characteristic Card(s), PID need to be created/modified/removed? (required for part with purchasing or incoming manufacturing controls)? | NA | No BUY part.
GA2.1.6 | 113 | DESIGN TRANSFER | 11.8 | Engineering Representative | Does this design change impact established Product Monitoring design transfer strategy: Requires update to Product complaint handling process/system (consider impact to PSI codes and associated information, e.g., PSI Code, PSI Description, LEGAL MFG, MFG SITE, DESIGN OWNER)? OR...Requires activities to define content of reporting e.g. regulatory traceable device identification, Device History Record and Inventory Control, and Annual Report Identification and Set-Up? OR...Requires activities to define GEHC site interactions, e.g., update Site ASL with new GEHC Site, Quality Agreement, oversight and monitoring methodologies? | NO | No impact for this release
GA2.1.6 | 114 | DESIGN TRANSFER | 11.9 | Manufacturing Representative | Does this design change affect eDHR or Paper DHR? | YES | A eDHR will be generated for this design change. | PRIOR TO ECO RELEASE
GA2.1.6 | 115 | DESIGN TRANSFER | 11.10 | Engineering Representative | Does this design change introduce a new or update to manufacturing Tool/software? | NA | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 116 | DESIGN TRANSFER | 11.11 | Engineering Representative | Does this design change impact released software delivery process? (e.g., physical media, duplication process, eDelivery process) NOTE: Ensure the released software can be reliably delivered from its archive to the point of use without corruption or unauthorized change. | NO | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 117 | DESIGN TRANSFER | 11.12 | Supplier Quality Representative | Do any of the impacted parts require Purchasing controls for established Essential Characteristics? | NA | No BUY parts with essential characteristics.
GA2.1.6 | 118 | DESIGN TRANSFER | 11.13 | Supplier Quality Representative | Does PQP need to be updated for any other reason besides Essential controls? | NO | Change does not add new suppliers or Buy parts, PQP not required.
GA2.1.6 | 119 | DESIGN TRANSFER | 11.14 | Supplier Quality Representative | Does this design change require new jigs/tooling/mould at the supplier, or is any of the existing jigs/tooling/mould at the supplier affected by this change? | NA | N/A product being in Cloud environment.
GA2.1.6 | 120 | DESIGN TRANSFER | 11.15 | Supplier Quality Representative | Does this design change impact Supplier test equipment, tools, simulators, software, product bays, products (used for testing/equipment qualification, etc.) used for manufacturing testing requiring update? If Yes, SCR is Required from Supplier for test equipment | NA | No supplier impact identified with this design change.
GA2.1.6 | 121 | DESIGN TRANSFER | 11.16 | Manufacturing Representative | Does this design change impact Production Process Validation, Equipment qualification, Tooling or Fixture verification, Manufacturing Software, Training, Packaging and Shipping (e.g. labeling, shelf life, storage requirements). Impacts Material handling procedures, Environmental Requirements (Shelf Life, Temperature, Humidity Controls, etc.) New chemical introduced/SDS impacted, Manufacturing Process Capability | NO | No impact on production process and no associated material elements for this DCP release.
GA2.1.6 | 122 | DESIGN TRANSFER | 11.17 | Supplier Quality Representative | Is the critical supplier not identified in current critical supplier list? If Yes, identify action for Engineering to update critical supplier list as needed. | NA | No critical suppliers identified with this supplier.
GA2.1.6 | 123 | DESIGN TRANSFER | 11.18 | Supplier Quality Representative | Is the critical supplier list not updated? If Yes, identify action for SQE to update ASL and notify suppliers of the critical supplier designation. | NA | No critical suppliers identified with this supplier.
GA2.1.6 | 124 | DESIGN TRANSFER | 11.19 | Supplier Quality Representative Sourcing Representative | Is the critical supplier list not updated? If Yes, identify action for Sourcing to update SQR (Supplier Quality Requirements). | NA | No critical suppliers identified with this supplier.
GA2.1.6 | 125 | DESIGN TRANSFER | 11.20 | Engineering Representative | Is the critical supplier list not updated? If Yes, identify action for RA to review/update Product Technical File as needed. | NA | No critical supplier involved
GA2.1.6 | 126 | DESIGN TRANSFER | 11.21 | Manufacturing Representative | Does this design change impact Dedicated Test Equipment (including SW options media stations)? | NA | No test equipment associated with this change
GA2.1.6 | 127 | DESIGN TRANSFER | 11.22 | Materials Representative | Is a buy-level part supplied by another GEHC site introduced with this change? NOTE: Check if the ECR introduces parts from a GEHC affiliate/supplier that is not on the site ASL. NOTE: Consider any updates required to the Site Product Matrix for new GEHC suppliers or new services provided by GEHC suppliers | NA | No BUY part
GA2.1.6 | 128 | DESIGN TRANSFER | 11.23 | Service Representative | Does this design change impact Proprietary Classification of Hardware/Software Tools, Documentation, and Files documented in Product Proprietary Classification record per QS_10001 Global Standard WI for Proprietary Classification (DOC1410674)? | NO | No changes to the Product Proprietary Classification Record
GA2.1.6 | 129 | DESIGN TRANSFER | 11.24 | Materials Representative | Does this design change impact Buy Parts? (Change To/Switching Supplier, New Direct Supplier Identified (Confirm Addition in ASL),New Sub-Tier Supplier Identified Part cost changing , Supplier Tooling changing) Does part categorization match supplier categorization, Approved Supplier List, Blanket Purchase Agreement, Purchase Order? | NA | NO BUY part
GA2.1.6 | 130 | Cleaning, Disinfection, and Sterilization | 12 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to Cleaning, Disinfection, and Sterilization design controls element? If NO, document the rationale for no impact. | NA | IPM application is a Non-Medical Cloud based SaaS application, and there is No Cleaning, Disfection and Serilization design control required. Hence, this is not applicable.
GA2.1.6 | 131 | Cleaning, Disinfection, and Sterilization | 12.1 | Engineering Representative | Does this design change impact chemicals listed in the user manual? Check https://cleaning.gehealthcare.com/ to ensure the chemicals listed match the GE Healthcare cleaning website. | NA | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 132 | Cleaning, Disinfection, and Sterilization | 12.2 | Engineering Representative | Does this design change impact established product cleaning and disinfection processes? If the design, materials, or device use has changed substantially, then a new validation or adoption assessment may need to be performed. Use GEHC_GQP_10.01.019_T001 Cleaning and Disinfection Plan Template (DOC2440136) [Device use change - if the device use has changed, then the Spaulding classification needs to be performed. If the Spaulding classification changes, then the cleaning and disinfection processes may need to be changed. Material change - probably does not affect the cleanability or disinfection but may have an effect on the material compatibility with the chemical. Design feature change - the change needs to be compared to the previous design feature to see if this is more difficult to clean and disinfect.] NOTE: Any addition or removal of cleaning agents requires assessment of Design input(SRS), Design output(Manuals), and Website. | NA | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 133 | TECHNICAL DESIGN REVIEW | 13 | Engineering Representative | Do any of the IMPACT ANALYSIS considerations/questions below apply to TECHNICAL DESIGN REVIEW design controls element? If NO, document the rationale for no impact. Refer to QS_4002 Global Standard WI for Technical Design Review (DOC0707915) for further guidance. | NA | No new feature is planned for this design change, hence no change and impact to TDR plan and related documents.
GA2.1.6 | 134 | TECHNICAL DESIGN REVIEW | 13.1 | Engineering Representative | Does this proposed design change implementation require TDR to be planned and reviewed by engineering SME (e.g., Chief Engineer, LSD, PEs, Architects)? If yes identify TDR as part of TDR Calendar or implementation action plan and identify required SME based on topic. Examples may include Reliability TDR, Safety TDR, Usability TDR, Manufacturability TDR, Serviceability TDR, Software TDR, Compatibility TDR, Interoperability TDR. | NO | No new feature is planned for this design change, hence no change and impact to TDR plan.
GA2.1.6 | 135 | TECHNICAL DESIGN REVIEW | 13.2 | Change Owner or Design Owner | Does this design change require TDR to be planned and executed per QS_3001 Global Standard WI for Suspended Mass Design (DOC1521734)? | NO | No new feature is planned for this design change, hence no change and impact to TDR plan.
GA2.1.6 | 136 | TECHNICAL DESIGN REVIEW | 13.3 | Engineering Representative Product Security Leader | Does this design change require TDR to be planned and executed per GEHC New Product Cybersecurity Standard (DOC2102581)? | NO | No Security related TDR is required as per the scope defined in "SW Change Set (Scope & Impact)" sheet.
GA2.1.6 | 137 | TECHNICAL DESIGN REVIEW | 13.4 | Engineering Representative | Does this design change require TDR to be planned and executed per GEHC New Product AI Quality Standard (DOC2252997)? | NA | No AI Quality TDR is required as per the scope defined in "SW Change Set (Scope & Impact)" sheet. Not applicable.
GA2.1.6 | 138 | TECHNICAL DESIGN REVIEW | 13.5 | Service Representative | Does this design change require TDR to be planned and executed per QS_1001 Global QS Standard WI for Product Service Standards (DOC0487759)? If YES Service TDR Guidance and Checklist (DOC2444001) should be used. | NO | No Service TDR is required as per the scope defined in "SW Change Set (Scope & Impact)" sheet.
GA2.1.6 | 139 | TECHNICAL DESIGN REVIEW | 13.6 | Engineering Representative | Does this design change require TDR to be planned and executed per GEHC Design Standard For Rechargeable DC Energy Storage Devices (Secondary Batteries and Super Capacitors) (DOC2385440)? NOTE: Design change impacting Safety and Charging parameters, storage and shelf life, portable power management, Portable power capacity, updates to PSP etc., may require TDR to be planned and approved before implementing design change. | NA | Not applicable for Non medical SaaS based cloud enviroment product.
GA2.1.6 | 140 | TECHNICAL DESIGN REVIEW | 13.7 | Engineering Representative | Are any additional reviews required? - Purchased GE Designed Parts/Assemblies - Design Requirements Review with Supplier - Documented Cross Functional Core Team Review - Manufacturing Review, - Regulatory Review - Marketing/Product Management or Clinical Review - Intellectual Property Review - Require Drawing review if this design is from Predicate device ? - Require Tolerance analysis for critical joints/assemblies ? | NO | No additional review is required as per the scope defined in "SW Change Set (Scope & Impact)" sheet. Not applicable.
GA2.1.6 | 141 | PART(S) DISPOSITION | 14 | Materials Representative | Actions to disposition impacted materials and product on-order, in-process, manufacturing, distribution, service spares (e.g., use-up, rework, scrap, no change, balance) is required? | NA | IPM application is a Non-Medical Cloud based SaaS application, and there is no material related impact required. Hence, this is not applicable.
GA2.1.6 | 142 | PART(S) DISPOSITION | 14.1 | Materials Representative | Does this Design Change Plan identify parts with "rework" and "scrap" disposition? If Yes, include action to identity rework instructions and capture evidence of rework and scrap as part of ERP Release or ECO implementation | NA | IPM application is a Non-Medical Cloud based SaaS application, and there is no material related impact required. Hence, this is not applicable.
GA2.1.6 | 143 | PART(S) DISPOSITION | 14.2 | Engineering Representative | Does this design change require Hold, Concession or Deviation to be initiated? If Yes, identify traceability to document number of Hold, Concession or Deviation. | NA | IPM application is a Non-Medical Cloud based SaaS application, and there is no material related impact required. Hence, this is not applicable.
GA2.1.6 | 144 | PART(S) DISPOSITION | 14.3 | Marketing Representative | Does this design change obsolete/end of life parts or catalogs or software or configurations or offerings as part of Product M6-M9 PRD milestone phase? If Yes, identify tasks to ensure impacts items are also obsoleted from order management/Marketing systems (e.g., Oracle, Salesforce). | NA | IPM application is a Non-Medical Cloud based SaaS application, and there is no material related impact required. Hence, this is not applicable.
GA2.1.6 | 145 | Other RDOs | 15 | Engineering Representative | Does this design change impact another modality, system or subsystem managed by another change board If NO, document the rationale for no impact. If YES, indicate required tasks to complete. | NO | Scope of this Design Change Release is limited to items as listed in "SW Change Set (Scope & Impact)" and there is no impact to other modalities , system, or sub-system managed by another change board. IPM Program manager will reach out to modality for announcement of this IPM Design change.
GA2.1.6 | 146 | Platform Software or Hardware | 16 | Engineering Representative | Does this design change impact Platform software or hardware? If yes, identify design controls deliverables required to be completed prior to change implementation (e.g., platform integration and integration testing activities) If NO, document the rationale for no impact. | NO | IPM application is a Non-Medical Cloud based SaaS application, and it does impact any Platform software or hardware. Hence there is no impact.
GA2.1.6 | 147 | OTHERS |  |  |  | NO